## wbs task management
Level | WBS code | WBS name | WBS description | Percent of work of the overall/parent deliverable | Budget | Assigned to
0 | 1 | Car manufacturing | All deliverables that need to be complete to manufacture a car | 100% | 27540 | Manufacturing manager
1 | 1.1 | Interior | Interior components of the car | 27% | 8720 | Team 1
2 | 1.1.1 | Seats | Cushions and adjusting mechanisms, including seat belts | 5% | 2100 | Jackson
2 | 1.1.2 | Upholstery | Seat covering and plastic fittings | 11% | 1122 | Jackson
3 | 1.1.2.1 | Seat covering | Fabric that will be used to cover seats | 6% | 670 | Jackson
3 | 1.1.2.2 | Plastic fittings | All other covering needed inside of the car | 5% | 452 | Sean
2 | 1.1.3 | Trunk | Space behind last row of seats | 4% | 3500 | Noah
2 | 1.1.4 | Steering system | Steering wheel and column | 7% | 1998 | James
1 | 1.2 | Body and exterior | Exterior and body components of the car | 51% | 10780 | Team 2
2 | 1.2.1 | Windshield | Shatterproof glass, defroster, and windshield wipers | 5% | 420 | Savannah
2 | 1.2.2 | Doors | Locking mechanism, door panels, and windows | 5% | 1500 | Tyler
2 | 1.2.3 | Roof | Includes optional rack and sun roof | 7% | 980 | Savannah
2 | 1.2.4 | Side panels | Metal frame and panels; does not include doors | 9% | 2290 | Savannah
2 | 1.2.5 | Undercarriage and wheels | Axles, transmission, exhaust, and suspension | 9% | 1780 | Ross
2 | 1.2.6 | Engine | Radiator, belts, spark plugs, filters, A/C unit, etc. | 10% | 3600 | Brittany
2 | 1.2.7 | Breaks | All parts related to car's breaking systems | 6% | 210 | Bridger
1 | 1.3 | Wiring and electronics | Wiring and electronic components of the car | 13% | 4540 | Team 3
2 | 1.3.1 | Lighting | Interior and exterior lighting | 2% | 850 | Luke
3 | 1.3.1.1 | Interior lighting | Dome lights | 1% | 100 | Luke
3 | 1.3.1.2 | Exterior lighting | Brights, blinkers, headlights, and fog lights | 1% | 750 | Luke
2 | 1.3.2 | Media features | Audio system, radio/cd player, cellphone ports | 7% | 1500 | Taylor
3 | 1.3.3.1 | Audio system | Speakers | 5% | 310 | Taylor
3 | 1.3.3.2 | Radio/CD player | Radio/CD player | 1% | 600 | Taylor
3 | 1.3.3.3 | Cellphone ports | USB/lighting connector ports on or near dashboard | 1% | 590 | Taylor
2 | 1.3.3 | Dashboard | Information, safety, and speed display | 4% | 1000 | Jessica
1 | 1.4 | Branding and Paint | Selection, preparation, application, and curing | 9% | 3500 | Team 4
2 | 1.4.1 | Painting | Selection of colours, body panel preparation, and application | 6% | 2500 | Cody
3 | 1.4.1.1 | Body preparation | Sanding, acetone wash, and taping | 3% | 1000 | Cody
3 | 1.4.1.2 | Paint application | Spray application and curing time | 3% | 1500 | Geneva
2 | 1.4.2 | Decal preparation | Selection of branding, cleaning location, digital layout, and apply | 3% | 1000 | Alex
3 | 1.4.2.1 | Digital layout | Graphic 3D rendition and layout approval | 1% | 500 | Alex
3 | 1.4.2.2 | Decal application | Soap and water preparation, decal application, and smoothing | 2% | 500 | Alex